## Sheet1
				Project Resla
Date	Descriptions	Actions	Problems	Solutions	Time-in	Time-out
25.02.2022	Discussion	Made technical draft	Not enough information about the project	We break down the project documentation into sections	10:10:00	10:50:00

14.03.2022	Planning	Made initial project plan	Uncertainty about the project	Figure out how the design will work	12:10:00	13:18:00

15.03.2022	Sep up remote connection	Debug camera and os, setup ssh	Debug camera working	Change raspberry os and sd card	12:50:00	16:15:00

16.03.2022	Attend project review	Setup github, ESP32, made the steering turn left/right.	Having trouble with code in the moodle	Modified the code by re-writing the code and then worked	08:40:00	16:55:00

23.03.2022	Working on RC car	Reconfigure code in the moodle	Several problems with the code in moodle make complexity on command	Study the code, and how servo working. Then modify the code in arduino	09:15:00	15:05:00

24.03.2022	Testing RC car	Adjusting the code	Strange behaviour of the RC car	We make a it function to working in the IoT lab environment	08:15:00	12:30:00

29.03.2022	Documentation	Added our project work properly documented and project review	For now the project is good probably future problems	Future solutions to future problems	08:30:00	12:45:00

31.03.2022	Set up the web server	To make the raspberry pi ip static and set up the web server on the raspberry	Having troubles with dynamic ip address, unable to make ip address static	Pip install flask	11:20:00	14:10:00